## Slide 1: Software Project Management
Introduction, Fundamentals, Classic Mistakes
1

## Slide 2: The Field
Jobs: where are they?
Professional Organizations
  Project Management Institute (PMI) (pmi.org)
  Software Engineering Institute (SEI)
  IEEE Software Engineering Group
Certifications
  PMI PMP
The “PMBOK” – PMI Body of Knowledge
Tools
  Ms Project

## Slide 3: PM History in a Nutshell
Birth of modern PM: Manhattan Project (the bomb)
1970’s: military, defense, construction industry were using PM software
1990’s: large shift to PM-based models
– 1985: TQM
  1990-93: Re-engineering, self-directed teams
  1996-99: Risk mgmt, project offices
  2000: global projects
Notes: New organizational structures, Considerable human resources, Extraordinary project leaders
https://www.planisware.com/hub/article/the-manhattan-project-project-management-during-difficult-times
Total quality management (TQM) is a structured approach to overall organizational management. The focus of the process is to improve the quality of an organization's outputs, including goods and services, through continual improvement of internal practices.
Business process reengineering is the act of recreating a core business process with the goal of improving product output, quality, or reducing costs.

## Slide 4: Job Fundamentals
Skills required
PM Positions and roles
The process

## Slide 5: Project Management Skills
Leadership
Communications
Problem Solving
Negotiating
Influencing the Organization
Mentoring
Process and technical expertise

## Slide 6: Project Manager Positions
Project Administrator / Coordinator
Assistant Project Manager
Project Manager / Program Manager
Executive Program Manager
V.P. Program Development

## Slide 7: Software Project Management
Management
Project Management
Software Project Management

## Slide 8: Software + Project + Management
Computer software, or just
software, is the collection of
computer programs and related data that provide the instructions telling a computer what to do

## Slide 9: Software + Project + Management
What’s a project?
PMI definition
  A project is a temporary attempt undertaken to create a unique product or service
Progressively elaborated
  With repetitive elements
A project manager
  Analogy: conductor, coach, captain

## Slide 10: Software + Project + Management
A project in business and science is a collaborative enterprise, frequently involving research or design, that is carefully planned to achieve a particular aim
Project Management
Project management is the application of knowledge, skills, tools, and techniques to project activities in order to meet or exceed stakeholder needs and expectations from a project.

## Slide 11: Dimensions of a Software Project
A software project has two main activity dimensions:
  engineering and Project Management.
  The engineering dimension deals with building the system and focuses on issues such as how to design, test, code, and so on.
  The project management dimension deals with properly planning and controlling the engineering activities to meet project goals for cost, schedule, and quality.

## Slide 12: Dimensions of a Software Project
For small projects an email may be fine, but for large commercial projects you need:
  Defined Processes, a degree of formality
  Tested and Documented processes
  To Secure the Quality of outcome

## Slide 13: Significance of Processes
 What is a Process?
Technically, a process for a task comprises a sequence of steps that should be followed to execute the task.

So, why we require Processes?
Processes represent collective knowledge. Using them increases your chances of success.
A process may have some extra steps, but you will not always know beforehand which ones are not needed, and hence you will increase your risks by taking shortcuts.

## Slide 14: Significance of Processes

Without processes, you cannot predict much about the outcome of your project.

You and the organization cannot learn effectively without having defined processes. Learning and improvement are imperative in today's knowledge-based world

Processes lower your anxiety level. The checklists inevitably cover 80 % of what needs to be done. Hence, your task reduces to working out the remaining 20 percent.

## Slide 15: Project vs. Program Management
16
What’s a ‘program’?
Mostly differences of scale
Often a number of related projects
Longer than projects
Definitions vary

## Slide 16: Factors affecting Software Projects

## Slide 17: Interactions / Stakeholders
As a PM, who do you interact with?
Project Stakeholders
  Project sponsor
  Executives
  Team
  Customers
  Contractors
  Functional managers

## Slide 18: PM Tools: Software
Low-end
  Basic features, tasks management, charting
  MS Excel, Milestones Simplicity
Mid-market
  Handle larger projects, multiple projects, analysis tools
  MS Project (approx. 50% of market)
High-end
  Very large projects, specialized needs, enterprise
  AMS Realtime (Adv Mngt Solution)
  Primavera Project Manager

## Slide 19: Tools: Gantt Chart

## Slide 20: Tools: Network Diagram

## Slide 21: PMI’s 9 Knowledge Areas
Project integration management
Scope
Time
Cost
Quality
Human resource
Communications
Risk
Procurement

## Slide 22: First Principles
One project size does not fit all
Patterns and Anti-Patterns
Spectrums
  Project types
  Sizes
  Formality and rigor (severity)

## Slide 23: Why Rapid Development
Faster delivery
Reduced risk
Increased visibility to customer
Don’t forsake quality

## Slide 24: Strategy
Classic Mistake Avoidance
Development Fundamentals
Risk Management
Schedule-Oriented Practices

## Slide 25: Four Project Dimensions
People
Process
Product
Technology

## Slide 26: Traditional Project Management Constraints
Triple Constraint
Scope
Time
Cost
o complete?
Every project has 3 constrains Scope goals: What work will be done? Time goals: How long should it take t Cost goals: What should it cost?

## Slide 27: Traditional Project Management Constraints
Time constraint may lead to less quality
because of ?
less time for analysis, less time for planning, less time for reviewing, less time for checking, less time for monitoring, less time for control,

## Slide 28: Traditional Project Management Constraints
Cost constraint may lead to less quality because of ?
Hiring less skilled people,
Getting less quality resources
Ignoring some customer requirements

## Slide 29: Traditional Project Management Constraints
Scope limitations may lead to less quality because of ?
Scope limitations may lead to Ignore some customer requirements
shortcuts

## Slide 30: Traditional Project Management Constraints
Time
Cost
Quality
Quadruple Constraint
Quality is a key factor for projects success
We may add Quality as a 4th constraint:
The Quadruple constraint =The Triple constraint +Quality
constraint
Scope

## Slide 31: Trade-off Triangle
Fast, cheap, good. Choose two.

## Slide 32: Trade-off Triangle
Know which of these are fixed & variable for every project

## Slide 33: People
“It’s always a people problem” Gerald Weinberg, “The Secrets of Consulting”
Developer productivity: 10-to-1 range
Improvements:
  Team selection
  Team organization
– Motivation

## Slide 34: People 2
Other success factors
  Matching people to tasks
  Career development
  Balance: individual and team
  Clear communication

## Slide 35: Process
Is process stifling?
2 Types: Management & Technical
Development fundamentals
Quality assurance
Risk management
Lifecycle planning
Avoid abuse by neglect

## Slide 36: Process contd.
Customer orientation
Process maturity improvement
Rework avoidance

## Slide 37: Product
The “tangible” dimension
Product size management
Product characteristics and requirements
Feature creep management

## Slide 38: Technology
Often the least important dimension
Language and tool selection
Value and cost of reuse

## Slide 39: Planning
Determine requirements
Determine resources
Select lifecycle model
Determine product features strategy

## Slide 40: Tracking
Cost, effort, schedule
Planned vs. Actual
How to handle when things go off plan?

## Slide 41: Measurements
To date and projected
  Cost
  Schedule
  Effort
  Product features
Alternatives
  Earned value analysis
  Defect rates
  Productivity (ex: SLOC)
  Complexity (ex: function points)

## Slide 42: Technical Fundamentals
Requirements
Analysis
Design
Construction
Quality Assurance
Deployment

## Slide 43: Project Phases
All projects are divided into phases
All phases together are known as the Project Life Cycle
Each phase is marked by completion of Deliverables
Identify the primary software project phases

## Slide 44: Lifecycle Relationships

## Slide 45: Seven Core Project Phases

## Slide 46: Project Phases A.K.A.
47

## Slide 47: Phases Variation
48
Concept Exploration
System Exploration
Requirements
Design
Implementation
Installation
Operations and Support
Maintenance
Retirement

## Slide 48: 36 Classic Mistakes
McConnell’s Anti-Patterns
Seductive Appeal
Types
  People-Related
  Process-Related
  Product-Related
  Technology-Related
Gilligan’s Island

## Slide 49: People-Related Mistakes Part 1
Undermined motivation
Weak personnel
– Weak vs. Junior
Uncontrolled problem employees
Heroics
Adding people to a late project

## Slide 50: People-Related Mistakes Part 2
Noisy, crowded offices
Customer-Developer friction
Unrealistic expectations
Politics over substance
Wishful thinking

## Slide 51: People-Related Mistakes Part 3
Lack of effective project sponsorship
Lack of stakeholder buy-in
Lack of user input

## Slide 52: Process-Related Mistakes Part 1
Optimistic schedules
Insufficient risk management
Contractor failure
Insufficient planning
Abandonment of plan under pressure

## Slide 53: Process-Related Mistakes Part 2
Wasted time during fuzzy front end
Shortchanged upstream activities
Inadequate design
Shortchanged quality assurance

## Slide 54: Process-Related Mistakes Part 3
Insufficient management controls
Frequent convergence
Omitting necessary tasks from estimates
Planning to catch-up later
Code-like-hell programming

## Slide 55: Product-Related Mistakes
Requirements gold-plating
  Gilding the lily
Feature creep
Developer gold-plating
  Beware the pet project
Push-me, pull-me negotiation
Research-oriented development

## Slide 56: Technology-Related Mistakes
Silver-bullet syndrome
Overestimated savings from new tools and methods
– Fad warning
Switching tools in mid-project
Lack of automated source-code control

## Slide 57: Reading
McConnell: Chapters 1-4
– We covered most of Ch 3 today
Schwalbe: chapters 1-2, 11 (344-345)

## Slide 58: Textbooks
Required texts
  “Rapid Development”, Steve McConnell
  “Information Technology Project Management”, Kathy Schwalbe
These provide two very different viewpoints
In-the-trenches vs. PMI textbook perspective
Recommended reading
  “Quality Software Project Management”, D. Shafer
  “Software Project Survival Guide”, Steve McConnell
  “Peopleware”, T. DeMarco and T. Lister